## Tracker Board
ID | Title | Owner | Type | Status | Priority | Team | Source | Notes | Created | Updated
1 | Fix account switcher on template project | Muhammad Ahmed | Bug/Fix | In Progress | High | Core API Team | Zoom - API Design & FE Updates (Mar 2) | Code is on staging, needs to be updated in template project. Test and release once merged. | 2026-03-02
2 | Test 5% markup on .be and .me environments | Priyanka | Action Item | In Progress | High | Core API Team | Zoom - API Design & FE Updates (Mar 2) | 5% markup working on staging. Need to verify on B and ME environments before production. | 2026-03-02
3 | Coordinate with Kirill to merge 5% markup to production | Priyanka | Action Item | In Progress | High | Auth / Backend | Zoom - API Design & FE Updates (Mar 2) | Frontend update depends on Kirill's backend PR being deployed first. | 2026-03-02
4 | Finalize and send developer communication email | Priyanka | Action Item | In Progress | High | HubSpot / Marketing | Zoom - Daily Catchup (Mar 2) | HTML and simplified versions prepared. Include new email ID requirement for account creation. Needs Ashkan's line-by-line review before sending. | 2026-03-02
5 | Deprioritize .me and .be domains — focus on .com | Ashkan | Product Decision | Done | High | Core API Team | Zoom - Daily Catchup (Mar 2) | Ongoing technical problems with .me and .be. Post note in team chat confirming focus on .com. | 2026-03-02
6 | Lipika to start Connected Apps on trader's dashboard | Lipika | Action Item | Backlog | High | Auth / Backend | Zoom - Daily Catchup (Mar 2) | Connected Apps first, API token tasks to follow. Ashkan to share task list for Lipika's team. | 2026-03-02
7 | Push back on mandatory 2FA for PAT creation | Ashkan | Product Decision | In Progress | Medium | Core API Team | Zoom - Daily Catchup (Mar 2) | Poor UX concern. Park the requirement for later discussion with Security team. | 2026-03-02
8 | Investigate app_id trade-capture gap in OptionDB | Eswara Battula | Bug/Fix | Blocked | High | BI / Data | Overseer - Zoom Meeting (Mar 2) | V2 app IDs (alphanumeric) not appearing in OptionDB. Legacy numeric app_id showing instead. Eswara to confirm with Data Engineering how V2 app IDs are persisted. BLOCKER: Cannot do post-migration reporting without this fix. | 2026-03-02
9 | Escalate missing V2 app_id in OptionDB to JB | Ashkan | Action Item | In Progress | High | Core API Team | Overseer - Zoom Meeting (Mar 2) | Post in channel summarizing that v2 app IDs are not present in OptionDB trade data. Tag JB, CC Priyanka and Eswara. | 2026-03-02
10 | Add detailed OptionDB query examples to escalation thread | Eswara Battula | Action Item | Backlog | High | BI / Data | Overseer - Zoom Meeting (Mar 2) | Reply in thread with sample queries, tables, examples showing legacy numeric app_id and missing v2 identifier. | 2026-03-02
11 | Remove redundant X button from UI | Priyanka | Bug/Fix | In Progress | Medium | Design (Figma) | Overseer - Zoom Meeting (Mar 2) | X button was not in approved design. Approve and communicate removal to implementing team. | 2026-03-02
12 | Fix permissions list not reflecting requested permissions | Priyanka | Bug/Fix | Backlog | Medium | Core API Team | Overseer - Zoom Meeting (Mar 2) | Permissions list mismatch. Investigate and provide fix or change request. | 2026-03-02
13 | Update dev documentation: distinguish app ID from client_id | Ashkan | Documentation | Backlog | Medium | Core API Team | Overseer - Zoom Meeting (Mar 2) | Internal documentation must clearly distinguish app ID (alphanumeric) from client_id parameter used with core. | 2026-03-02
14 | Provide test account/client IDs to Eswara for trade validation | Priyanka | Action Item | In Progress | High | BI / Data | Overseer - Zoom Meeting (Mar 2) | Send correct test account details to validate trades and confirm what identifier appears in OptionDB. | 2026-03-02
15 | Clarify decision: cashier/P2P APIs remain internal | Ashkan | Product Decision | In Progress | Medium | Core API Team | Zoom - API Design & FE Updates (Mar 2) | Write comment in channel clarifying decision not to expose cashier and P2P APIs externally. Address queries from Sephan and Rakshish. | 2026-03-02
16 | Share PAT task list for Lipika's team | Ashkan | Action Item | Backlog | Medium | Auth / Backend | Zoom - API Design & FE Updates (Mar 2) | Include PAT creation and revocation inside Trader's Hub. Connected Apps implementation first. | 2026-03-02
17 | Manros: finalize app builder design review | Manros | Review | In Progress | Medium | Design (Figma) | Zoom - API Design & FE Updates (Mar 2) | Complete final review so Nigel can pick it up this week. | 2026-03-02
18 | Coordinate affiliate tagging for March commissions | Priyanka | Action Item | Backlog | Medium | Partners / Biz Dev | Zoom - API Design & FE Updates (Mar 2) | Coordinate with Kirill and relevant teams to finalize when affiliate tagging can be added for partners. | 2026-03-02
19 | Coordinate with Kirill to provide details to Govi | Priyanka | Action Item | Backlog | Medium | Auth / Backend | Zoom - API Design & FE Updates (Mar 2) | Required details for commission calculation. | 2026-03-02
20 | Prepare sunset date communication email | Priyanka | Action Item | In Progress | High | HubSpot / Marketing | Meeting - AN-PS (Feb 25) | Coordinate setup with Manahil in HubSpot. Email needs proofreading by Ashkan, Rakshit, Prakash, and Azita before sending. | 2026-03-02
21 | Follow up with Aline (compliance) on required links | Priyanka | Action Item | In Progress | Medium | Compliance / Legal | Meeting - AN-PS (Feb 25) | Get required links and update as needed for compliance requirements. | 2026-03-02
22 | Remove payment agent option from legacy API signup | Muhammad Ahmed | Action Item | In Review | Medium | Core API Team | Meeting - AM-PS (Feb 24) | Keep only affiliate option. Priyanka to test login and signup flow after changes. Push to production when ready. | 2026-03-02
23 | Add TNC to current dashboard before 5% markup push | Manros | Action Item | In Progress | High | Design (Figma) | Meeting - API Design & FE Updates (Feb 25) | New terms and conditions to be added to current dashboard. Must be done when 5% markup is pushed. | 2026-03-02
24 | Implement email notification on app registration | Backend team | Action Item | Backlog | Medium | Auth / Backend | Meeting - API Design & FE Updates (Feb 25) | When new app is registered, email with T&C sent to user. Triggered on app creation event. Priyanka to coordinate with Kirill to identify the event. | 2026-03-02
25 | Remove AI disclaimer from V2 | Priyanka | Action Item | In Progress | Low | Compliance / Legal | Meeting - API Design & FE Updates (Feb 25) | Ashkan requested removal. Priyanka to convey to compliance and handle. | 2026-03-02
26 | Update OAuth consent page content and design | Muhammad Ahmed | Action Item | Backlog | Low | Core API Team | Meeting - API Design & FE Updates (Feb 25) | Minor change. Not blocking but needs coordination with Lepika/Swissen/Aizat. New text provided, Manros creating new design. | 2026-03-02
27 | V2 commission calculation: exclude app markup to prevent overpayment | Ying Shan | Action Item | Backlog | High | Partners / Biz Dev | Meeting - Commissions (Feb 24) | Remind Govi to ensure V2 option commission calculations exclude app markup amount. Critical to avoid overpaying partners. | 2026-03-02
28 | Check JB validation for markup values above 3% | Ashkan | Action Item | In Progress | High | Auth / Backend | Meeting - Commissions (Feb 24) | Message JP to double check if validation would reject markup/commission values above 3% before proceeding with 5% update. | 2026-03-02
29 | Schedule follow-up with Tristan and Govi on partner commissions | Ashkan | Action Item | Backlog | Medium | Partners / Biz Dev | Meeting - Commissions (Feb 24) | Assign responsibility and coordinate calculation/handling of partner commissions for V2. Need to finalize within 1-2 weeks. | 2026-03-02
30 | Talk to Bilal about linking Deriv accounts to partner accounts | Ashkan | Action Item | Backlog | Medium | Partners / Biz Dev | Meeting - Commissions (Feb 24) | Users need universal identity for dev portal and partner site. Will help solve payment-related issues. | 2026-03-02
31 | Confirm V2 captures all commission/markup data per trade | Kok (JB) | Action Item | In Progress | High | Auth / Backend | Meeting - Commissions (Feb 24) | Double check that V2 records all necessary commission/markup data and no validation prevents values above 3%. | 2026-03-02
32 | Cloudflare configuration for V2-enabled country routing | Muhammad Ahmed | Action Item | Blocked | High | DevOps / IT Ops | Meeting - MA-PS (Feb 24) | V2 users need manual redirect to legacy API to see banner and sign up. Tag Amam to prioritize. BLOCKER: Waiting on Amam's effort estimate. | 2026-03-02
33 | Add TNC checkbox per app in registration flow | Manros | Action Item | Backlog | Medium | Design (Figma) | Meeting - Manros-PS (Feb 25) | Required checkbox for T&C acceptance during app registration. Apply to both beta dashboard and new dashboard. Per-app, not per-user. | 2026-03-02
34 | Provide legacy API link description to Muhammad | Priyanka | Action Item | Done | Low | Core API Team | Meeting - MA-PS (Feb 25) | One-liner description for Legacy API link with external link icon. Muhammad to incorporate into PR. | 2026-03-02
35 | Disable Telegram channel public discussions | Ashkan | Product Decision | In Progress | Medium | Support (Intercom) | Meeting - AN-PS (Feb 25) | Direct users to submit tickets for questions. Handle inquiries privately. Agreed to consult with Varun on communication strategy. | 2026-03-02
36 | Coordinate release with Roanoke — all traffic to legacy-api.dev.com | Ashkan | Action Item | Done | High | Core API Team | Meeting - AN-PS (Feb 25) | Unified release strategy. All traffic goes to legacy-api.dev.com initially. | 2026-03-02
37 | Point new signups to developers.deriv.com once stable | Ashkan | Action Item | Backlog | Medium | Core API Team | Meeting - AN-PS (Feb 25) | After confidence in new setup (Thursday/Friday or when stable). Coordinate with deriv.com team. | 2026-03-02
38 | Kirill: provide eventbus endpoints for app state replication | Kirill | Action Item | Done | High | Auth / Backend | Slack - #task_apiv2_markupcommissions | Endpoints shared: devhub.app_created.v1, devhub.app_updated.v1. Data to be provided to Govi. | 2026-03-02
39 | Provide data to Govi for commission calculation | Kirill / Ying Shan | Action Item | In Progress | High | Auth / Backend | Slack - #task_apiv2_markupcommissions | Priyanka asked Kirill and Ying Shan to provide data to Govi. | 2026-03-02
40 | Handle partner complaints about 5% rollout via direct calls | Ashkan | Action Item | In Progress | High | Partners / Biz Dev | Zoom - Daily Catchup (Mar 2) | Prepare responses and join partner calls. Confirm P2P signup support in messaging. | 2026-03-02
41 | Octomind test integration for DAPI-905 | Bertrand | Action Item | In Progress | Medium | Core API Team | Slack - #task_api_v2_website | Bertrand working on Octomind test integration. | 2026-03-02
42 | Fix staging URLs for deriv.be/deriv.me | Matin | Bug/Fix | In Progress | Medium | Core API Team | Slack - #task_api_v2_website | Ongoing issues with staging URLs. Now deprioritized per today's decision to focus on .com. | 2026-03-02
43 | Fix CNAME/redirect issues | Prince | Bug/Fix | In Progress | Medium | DevOps / IT Ops | Slack - #task_api_v2_website | CNAME and redirect issues being addressed. | 2026-03-02
44 | Design migration banner and dashboard | Manros | Action Item | In Progress | Medium | Design (Figma) | Slack - #task_api_v2_website | Migration banner design for developers.deriv.com. | 2026-03-02
45 | Review Priyanka's announcement email line by line | Ashkan | Review | Backlog | High | Core API Team | Zoom - Daily Catchup (Mar 2) | Return feedback/approval on HTML and simplified versions of the Rediff API announcement email. | 2026-03-02
46 | JP to review trade-capture path for testing app_id | JP | Action Item | Backlog | High | Auth / Backend | Zoom - Daily Catchup (Mar 2) | Dependency: Assessment of options trade-capture for app_id (testing app) and remediation plan. | 2026-03-02
47 | Duplicate account policy: communicate SOP changes | Priyanka | Action Item | Backlog | Medium | Support (Intercom) | Slack - #api_customer_support | Discussions with Ashkan, Dmitry about duplicate account policy for API developers. SOP changes needed for V1 vs V2 ticket routing. | 2026-03-02
48 | Set up Intercom inbox automation for api-support@deriv.com | Dmitry | Action Item | Backlog | Medium | Support (Intercom) | Slack - #api_customer_support | Automate API support ticket routing. | 2026-03-02
49 | Send first incentive communication to top 50 developers | Priyanka | Action Item | Backlog | High | HubSpot / Marketing | Meeting - AN-PS (Feb 25) | V1 total + 20% on V2. Target V2-enabled countries. Separate communication to all developers on Monday. | 2026-03-02
50 | Prepare timeline for 5% markup revert to 3% | Ashkan | Action Item | Backlog | Medium | Core API Team | Meeting - Commissions (Feb 24) | 5% through March or April, then revert to 3%. Need clear timeline communicated to partners. | 2026-03-02
51 | Update documentation: make 5% markup commission more visible | Priyanka | Documentation | Backlog | Low | Core API Team | Meeting - AN-PS (Feb 23) | Update the documentation as discussed to highlight the 5% markup commission. | 2026-03-02

## Dashboard
Deriv API V2 — Live Team Tracker
Last sync: Mar 2, 2026 3:30 PM · Sources: Slack (7 ch) · Overseer · Zoom · Project Files
21 | 23 | 2 | 1 | 4
Backlog | In Progress | Blocked | In Review | Done
By Team
Team | Total | In Progress | Blocked | Done
Core API Team | 18 | 7 | 0 | 3
Auth / Backend | 10 | 4 | 0 | 1
Design (Figma) | 5 | 4 | 0 | 0
Partners / Biz Dev | 5 | 1 | 0 | 0
HubSpot / Marketing | 3 | 2 | 0 | 0
BI / Data | 3 | 1 | 1 | 0
Support (Intercom) | 3 | 1 | 0 | 0
Compliance / Legal | 2 | 2 | 0 | 0
DevOps / IT Ops | 2 | 1 | 1 | 0
By Owner
Owner | Total | High Priority | In Progress | Blocked
Priyanka | 15 | 6 | 8 | 0
Ashkan | 15 | 6 | 6 | 0
Muhammad Ahmed | 4 | 2 | 1 | 1
Manros | 4 | 1 | 3 | 0
Eswara Battula | 2 | 2 | 0 | 1
Lipika | 1 | 1 | 0 | 0
Backend team | 1 | 0 | 0 | 0
Ying Shan | 1 | 1 | 0 | 0
Kok (JB) | 1 | 1 | 1 | 0
Kirill | 1 | 1 | 0 | 0
Kirill / Ying Shan | 1 | 1 | 1 | 0
Bertrand | 1 | 0 | 1 | 0
Matin | 1 | 0 | 1 | 0
Prince | 1 | 0 | 1 | 0
JP | 1 | 1 | 0 | 0
Dmitry | 1 | 0 | 0 | 0

## Team Scratchpad
Team Scratchpad — Open Questions, Decisions & Dependencies
Core API Team
| Open Questions | Decisions Made | Dependencies
1 | Should we support .me and .be or fully deprioritize? | Deprioritize .me and .be — focus on .com | JB: Store V2 app_id in OptionDB
2 | When will new signups be pointed to developers.deriv.com? | Cashier/P2P APIs remain internal | Kirill: Backend PR for 5% markup
3 | What is the timeline for 5% markup revert to 3%? | Push back on mandatory 2FA for PAT creation | Ahmed: Account switcher fix
4 |  | 5% markup live — revert to 3% in April | JP: Trade-capture path review
BI / Data
| Open Questions | Decisions Made | Dependencies
1 | How are V2 app IDs persisted in trading data? | Post-migration measured by trading KPIs not signups | Data Engineering: V2 app ID persistence
2 | Is markup recorded for alphanumeric app IDs? | Legacy numeric app_id cannot be used for V2 reporting | Core team (Ronak): Column mapping and backfill
Auth / Backend
| Open Questions | Decisions Made | Dependencies
1 | Will JB validation reject markup above 3%? | Lipika starts Connected Apps first, API tokens follow | Kirill: 5% backend PR to production
2 | When can Lipika start Connected Apps? | Email notification on app registration with T&C | Kirill: Eventbus endpoints data to Govi
Partners / Biz Dev
| Open Questions | Decisions Made | Dependencies
1 | Who calculates V2 partner commissions long-term? | 5% commission (temp), revert to 3% later | Govi: V2 markup payment handling
2 | How to link dev accounts to partner accounts? | Extra 2% from client's bucket, not company's | Bilal: Account linking
3 |  |  | Tristan: Commission process
HubSpot / Marketing
| Open Questions | Decisions Made | Dependencies
1 | When is HubSpot email setup ready? | Email needs multi-level review before sending | Manahel: HubSpot setup
2 |  | Top developers first, then all developers | Ashkan: Line-by-line email review
Design (Figma)
| Open Questions | Decisions Made | Dependencies
1 | Where to place T&C in new dashboard? | T&C checkbox per app, not per user | Manros: App builder design for Nigel
2 |  | X button removed from UI | Manros: Migration banner design
Support (Intercom)
| Open Questions | Decisions Made | Dependencies
1 | How to identify API partners vs regular developers? | Disable Telegram public discussions | Dmitry: Intercom inbox automation
2 | SOP for V1 vs V2 ticket routing? | Handle inquiries privately

## Sync Log
Sync Log — Data Source History
Timestamp | Source Type | Source Name | Items Added | Notes
2026-03-02 15:30 | Slack | #project_deriv_api_v2 | 14 | Weekly priorities, V2 dashboard errors, developer feedback
2026-03-02 15:30 | Slack | #api_customer_support | 3 | Duplicate accounts, Intercom automation, ticket routing
2026-03-02 15:30 | Slack | #task_apiv2_markupcommissions | 2 | Eventbus endpoints, data for Govi
2026-03-02 15:30 | Slack | #task_api_v2_website | 5 | Octomind, staging URLs, CNAME fixes, migration banner
2026-03-02 15:30 | Slack | #task_apiv2_hubspot | 0 | New channel — no messages yet
2026-03-02 15:30 | Slack | #task_apiv2_seo | 0 | New channel — no messages yet
2026-03-02 15:30 | Slack | #task_apiv2_partners | 0 | New channel — no messages yet
2026-03-02 15:30 | Email | Overseer Meeting Minutes | 12 | 4 meeting summaries from Feb 27 + Mar 2
2026-03-02 15:30 | Email | Zoom Meeting Assets | 8 | API Design & FE Updates, Daily Catchup (Mar 2)
2026-03-02 15:30 | Files | Project Docs (12 recent) | 15 | AM-PS, AN-PS, MA-PS, Manros-PS, Commissions, API Design meetings

## Sync Config
Sync Source Configuration
Slack Channels
Channel | Channel ID | Status | Last Synced
#project_deriv_api_v2 | C08H3AYCDM3 | Active | 2026-03-02
#api_customer_support | C0A7NK0S5N3 | Active | 2026-03-02
#task_apiv2_markupcommissions | C0AJASV065P | Active | 2026-03-02
#task_api_v2_website | C09QFK3SA5V | Active | 2026-03-02
#task_apiv2_hubspot | C0AJ0DSSYEA | New | 2026-03-02
#task_apiv2_seo | C0AJ2GAK142 | New | 2026-03-02
#task_apiv2_partners | C0AHW8DNX8B | New | 2026-03-02
Email Sources
Source | Filter | Status | Last Synced
Overseer Meeting Minutes | from:overseer@deriv.com | Active | 2026-03-02
Zoom Meeting Assets | from:no-reply@zoom.us | Active | 2026-03-02
Project Files
Path | API Meetings & Notes (75 docs)
Recent synced | 12 docs from last 7 days